## Slide 1: Te Ara Whetū Update
Waikanae Community Board Tuesday 19 November 2024

## Slide 2: programme
Detailed design
Building consent
Developed design
Construction
Opening
Resource consent lodged
By end of 2024
Procurement of main contractor
Early 2025
Design brief
9
2
February to April 2024
Building investigation
3
March to April 2024
Studio Pacific engaged
1
February 2024
Demolition & decontamination
4
April to June 2024
Concept design
5
May to September 2024
Preliminary design
October to December 2024
7
Community engagagement
September 2024
6
11
March to July 2025
12
Mid-2025
10
December 2024 to March 2025
13
Mid-2025 to late 2026
14
Late 2026
8

## Slide 3: Latest Plans - Ground Floor

## Slide 4: Latest Plans – Level 1

## Slide 5: Latest Plans – Level 2

## Slide 6: Community engagement
During the week of 9 to 14 September, we invited the community into the old library to view the concept designs.
The objectives of the engagement were to:
show people how their comments influenced the design
inform about next steps and timeline
Give people an opportunity to comment (but no further chance to influence).

## Slide 8: Community Engagement
Hundreds of people called in during the week. They were eager to see the proposed layout and overwhelmingly liked what they saw.
We received 138 comments:
  76 were general praise of the concept design
  10 related to specific features
  3 positive comments about the engagement process and 2 about the name
  16 suggestions about the building
  16 comments about the library's operations
  9 comments about the specific needs of teenagers.

## Slide 9: Next Steps
By the end of 2024 we hope to have lodged the Resource Consent and completed detailed design.
In early 2025 we aim to tender for the main construction contractor.
Construction is currently anticipated to commence mid-2025 with an estimated construction period of 12-18 months.
If all goes to plan we will open Te Ara Whetū in late 2026.

## Slide 10: QUESTIONS